## Info
N_Brabant contains the improvement planned for the N Brabant model.
N_Brabant_minor includes minor option changes, which don't constitude a large improvement task on their own.
Categories contains a categories table for the other tabs. It's not used for Data Validation ATM, but I find it useful as a category overview.

## NBr
Improvement | Improvement Catgory | Categories Secondary | Pros | Cons | Data Requirements | Reason for Current Absence | Final Decision For/Against Improvement | Implementation plan | Priority | Importance | Time Estimate (weeks) | Week of start | Week of end | Comments | Date of completion
Creation of RunLog & RunMng code | Workflow Streamlining Model Understanding | QA | -Organised and documened runs. -Decrease errors and reduces confusion in the future | -Time investment. -Creating and filling run-log. | - | It's considered not-necessary by some. | Yes. Simple task with large impact. | -Use previous experience. -Work in parallel with understanding the model and restructuring folders. | 10 | 9 | 1.5 | -2 | 3 | IMO it's essential to record and document Sims in a clean and organised manner, to avoid future confusion and potential mistakes. For that reason I'll make a spreadsheet catalog for all our Sims and a governing script that will run the model based on the spreadsheet.
Folder/Worklow re-structure | Workflow Streamlining Model Understanding | QA | -More effective file grouping. -Saves time in the long run. | -Requires initial time investment. | - | Folder structure is personal preferene. | Yes. Simple task with large impact. | -Restructure while understanding model and creating run-log. -Categorize folders thematically. | 10 | 8 | 0.5 | -2 | 3 | This works in combination with the use of MdlNs. It's an overall system for keeping track of changes.
Automation of model output visualisation & output comparison | Workflow Streamlining Model Understanding | QA | -Saves manual labor time. -Ensures identical processing of outputs. | -Set-up time. -Extensive QA required as errors will be recreated. | Model outputs, available at the time of writing. | I'll ask Eva if she uses something like that, but even still, we'll probably want to add things to it for our project. | Yes. Practical. | -Write script to Vis test run. -Add SmB script. | 10 | 9 | 3 | -2 | 3 | Need a script for standard model output Vis and comparison of B and S Sims. Extra Vis can be
Implementation of unstructured grids [SG -> UsG] | Spatial Resolution | Computational Efficiency | -Refined resolution at areas of interest. -Easier convergence, especially at non-linear areas. | -Time/effort for conversion. -Confusion cause of spatial comlexity. | Features of importance. | Method novelty and complexity. | No. Complicated, high risk (in terms of time) task. | -'I'll only spend a few hours exploring the advantages of UsG over SG for future use. | 9 | 4 | 5 | 3 | 3 | Highly unlikely we'll implement this given how time consuming and risky it is.
Time-series update | Temporal Data Extension | Calibration/Validation | -Updated model. -Historical-prediction TS continuity. | -Time/effort. -Data requests. | Extended TS for temporal parameters. | Model hasn't been updated. | Yes. There must be continuity with KNMI TS. | -Make a table containing all temporal input. -Get missing files/dates and extend list of references for model input. | 8 | 7 | 1.5 | 3 | 4.5 | Might be unecessary. Depends on when KNMI TS start and when historical Mdl TS end.
GWH calibration improvement | Calibration/Validation Uncertainty Quantification | Parameter Estimation | -Model validation. -Reduced uncertainty. | -Time/effort. | Additional GWH data, especially at areas of interest. | Calibration requirements were potentially lower. | Yes. GWH Clb needs to be improved and maintained through other changes. | -Investigate input uncertainty. -Develop calibration algorithm/process. | 7 | 6 | 2 | 4.5 | 6.5 | The earlier the calibration procedure is set-up, the better. But the calibration will be under review throughout the improvement proccess. We'll also work on this in parallel when calibrating the Str
Spatial Model Subsetting | Spatial Extent | Computational Efficiency | -Reduced run-time. -Focus on areas of interest - reduction of model area. -Improved future time investment. | -Limiting output to specific area. -Might need to make more/new assumptions about boundary conditions. | Probably none, as cut-down model will be subset of original model. | Full model covers larger region. | Yes. Focus on smaller area. | -Identify areas of interest for WS. -Think about boundary conditions. -Draw polygon and subset the model using iMOD. | 6 | 10 | 1.5 | 6.5 | 8 | Working with the full model extend is a redundant computational burden and won't let us focus that well on the areas of ineterest. After we've run the model once, it'
Dynamic representaton of streams [RIV -> SFR (or RibaSim)] | Process Represenation Model Integration | Parameter Estimation Uncertainty Quantification | -Allows dynamic calculation of stream stages. -Streamflow routing performed. -Allows simulation of river flood, flow attenuation, and accumulation of tributary flows. -Allows calibration/validation of stream flows. -More stream parameters. | -Additional conceptual complexity. -Increased computational demand. -Additional data requiremnts (routing connections, channel parameters etc). -Time/effort for conversion. -Time/effort for convergence & valiation satisfaction. | Stream parameters (if not possible to infer them from RIV data). | It's a GWM, we want an integrated model. | Yes. It's in the PhD title. | -Understand if SFR/RibaSim can work with the rest of the model set-up. -Compare pros and cons of two options. -Creat necessary input files. -Connect with the ret of the model. | 5 | 10 | 5 | 8 | 16 | Currently (with RIV) streams are boundary conditions for a GWM. (cause RIV doesn't do river stage calcs or routing). With the SFR, streams are part of an integrated model. We need to also consider if we'll go for SFR or RibaSim.
Implementation of anisotropic Str-Aqf conductance | Process Represenation | Calibration/Validation | -Conceptual improvement/addition. -Enables improved calibration (in some cases). | -Requires parameter estimation. | Parameter range from literature and/or field data. | Was represented by RIV+DRN. | Yes. Necessary for good calibration. | -Check if SFR/RibaSim can do this (this is important for chosing which of the two to use). -Understand how anisotropic the conductance needs to be. -Use conductance from RIV package for Str->Aqf. Increase by amount leaving for DRN for Aqf->Str. | 5 | 7 | 1 | 8 | 16 | Aqf->Str Cond > Str->Aqf Cond (I believe this is accepted within the field).
Re-enable WOFOST | Process Represenation] Model Integration | Calibration/Validation | -Dynamic calculation of crop growth (yield and water demand). | -Time/effort for model coupling. | Crop growth parameters (if not available) | There seems to be a WOFOST model version | Yes. Important for Agriculture optimization Ch. | -Learn how this was done for the model manual. -Find inputs/options they used. -Apply/enable them. | 5 | 7 | 2 | 8 | 16 | Based on the model manual, this doesn't cause too much difference, but in cases of extreme drought, it might. This is also useful for the Agriculture optimization Ch, as crop yield damage can be calculated.
Utilization of Multi-core MF | Computational Efficiency | Workflow Streamlining | -Greatly improves single Sc performance. | -Technically complex. -Requires additional external communication. | Multi-core MF version. | Already included in iMOD. | Currently not available with SFR. If we use RibaSim, I have to check if it can be used. | -Check if it's possible to implement it at this point. -If it is, it shouldn't be hard to implement this. Otherwise, just skip it. | 4 | 2 | 1.5 | 16 | 16 | Meaning performing one run on multiple cores. Multiple runs on multiple cores is quite easy. Hard to estimate cause it's a very new method. Not sure if it even works with iMOD.
Stream discharge calibration improvement | Calibration/Validation Uncertainty Quantification | Parameter Estimation | -Model validation. -Reduced uncertainty. | -Time/effort. | Stream discharge dataset. | Streams weren't calculated. | Yes. Important for Str flow predictions. | -Create algorithm, similar to head calibration. -Might be worth combining the two. | 3 | 9 | 3 | 16 | 19 | The earlier the calibration procedure is set-up, the better.
Improvement of Irrigation Time-step | Process Represenation | - | -Improves temporal aspect of irrigation abstractions. | -Time investment to implment and review calibration. | - | Implementation complexity. | Yes/Maybe. We'll try to do it. If it's too hard, we'll reconsider. | -Find relevant MetaSWAP-Wofost setting and change it. | 2 | 8 | 2 | 19 | 21 | 10-day time-steps for irrigation actions are quite long.
Surface Runoff: Hourly infiltration limit | Process Represenation | Parameter Estimation | -More realistic distribution of precipitation. | -Requires hourly Prcp and PET data used in daily model time-step. | Hourly Prcp and PET data TS. | Rarely activated process that is hard to implement in the model. | Yes, we'll investigate how hard this is (if possible), then maybe we'll implement it. | -Check availability of hourly infiltration data. -Devlop and apply method for hourly infiltration limit check. | 1 | 5 | 1 | 21 | 22 | Hard to implement and only contributes towards very wet end of the spectrum. Good to have, but low in priority and importance.
Note on J1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-10. 10 being highest.
Note on K1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1-10. 10 being highest importance.
Note on M1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Week number starting from the first full week of January - as was planned in the PhD proposal Gantt chart. Reply: Numbers in parenthesis symbolize a potential earlier/later start. i.e. GWH calibration being checked in parallel with everything else until the end of the improvements.
Note on N1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Numbers in parenthesis symbolize a potential earlier/later start. i.e. GWH calibration being checked in parallel with everything else until the end of the improvements.
Note on O2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The sooner this is implemented, the easier our life becomes. Hence urgency in terms of priority.
Note on O3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What I mean is you can (and should) have multiple files of the same type in the same folder and they won't get confused for one another cause their name will contain the run number.
Note on H5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Highly unlikely we'll do this. Would have more advantages if we were building a model from scratch.
Note on J5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This needs to happen first. Otherwise we'll have to almost repeat the other improvements.
Note on K5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to do more research on it: 1. Check how dense features (drainage, wells etc.) are compared to the model grid. 2. Investigation/Literature Review on improvements of UsG.
Note on F6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: At least up to the start of the KNMI'23 Sc TS.
Note on I7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Might be worth using some automated process like PEST, but only after adding SFR, so that both can be calibrated at the same time.
Note on J7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Could be lower if Deltares are going to work on this anyway. (then we can simply "steal" their improvements.)
Note on K7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Depends on how good the calibration is. If it's currently not good enough, then this can be as high as 9.
Note on A9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Or D-HYDRO.
Note on B9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Model Integration: This change makes it an integrated model from a GW model.
Note on E9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: I have experience with creating routing networks. Channel parameters can be calculated off of existing RIV parameters, but its probably better to get the detailed data as it'll help with the calibration of Str flows.
Note on I9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Don't forget to check if SFR/RibaSim can do anisotropic stream conductance.
Note on O9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Current way of calculating Str Rch or GW seepage (NetRCH= ∆lvgmodf*sc1-qmodf ) needs to be removed, as Str Rch/GW seepage will now be calculated by SFR. (Check Brabant model documentation for more info). Reply: As I understand SFR and RibaSim work similarly, but I don't know much about RibaSim. On About iMOD - iMOD - oss.deltares.nl it says that SFR doesn't work with iMOD Suite, so RibaSim might be the only option currently. But I need to double check this. Or we could use iMOD 5 instead of suite.
Note on G10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: There might be a better way to do this with the SFR package. Use of DRN for this isn't ideal.
Note on H10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: There might be a better way to do this with the SFR package. Use of DRN for this isn't ideal, but it can probably work as a back-up.
Note on H12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Unless we use RibaSim instead of SFR, which will probably work with the multi-core solver.
Note on J12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Higher if on values having decreased runtimes ASAP.
Note on K12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: It's nice to have a Mdl that runs fast, but it's not necessary.
Note on K13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Much higher that GW, cause we know Str Dis has never been calibrated (in this Mdl).
Note on O13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Stream calibration is more complicated than head calibration by nature (more dynamic) and on top of that we're starting from scratch (while GWH calibration has been performed).
Note on F14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Can't think of any at the time of writing, but I don't understand the process well enough yet.
Note on I14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If this is part of the compiled code, then this becomes much harder. Unless we get in contact with the right people.
Note on O14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Search for "The rotational period is 10 days " in the SIMGRO (MetaSWAP) manual.
Note on A15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Infiltration capacity per day may be enough, but hourly might NOT be. This leads to more runoff. Reply: Also when GWL above surface. Reply: Ponding depth 2-10mm.
Note on I15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For hourly data, try Meteorological datasets NHI

## SFR_requirements (hidden)
# | Parameter | Details | Block | Required? | Already available?
| rlen |  | PACKAGEDATA | 1
| rwid |  | PACKAGEDATA | 1
| rgrd |  | PACKAGEDATA | 1
| rtp |  | PACKAGEDATA | 1
| rbth |  | PACKAGEDATA | 1
| rhk |  | PACKAGEDATA | 1
| man |  | PACKAGEDATA | 1
| ncon |  | PACKAGEDATA | 1
| ustrf |  | PACKAGEDATA | 1
| ndv |  | PACKAGEDATA | 1
| Routing Network | The upstream and downstrem reach(es) of each reach need to be specified in the CONNECTIONDATA block. | CONNECTIONDATA | 1 | 0
| Cross-sections |  | CROSSSECTIONS
| sfrsetting |  | DIVERSIONS

## NBr_TS_Ext
Parameter | N of files present | File Type | Min Av Date | Max Av Date | Last Date - Exception | TS | Data extend needed? | Extended? | Reference extend needed? | Referenced extended files? | Details
Precipitation |  | .asc | 1980-01-01 | 2020-10-05 |  | Daily | Proably no |  | Yes
Evaporation |  | .asc | 1980-01-01 | 2020-10-05 |  | Daily | Proably no |  | Yes
meteo-other | 4749 | .asc | 2007-01-01 | 2020-01-01 |  | Daily | Proably no
WEL-Ind_Aa_and_Maas | 17 | .txt | 1976-01-01 | 2018-01-01 | 2026-01-01 | Yearly | Maybe |  | No |  | There is one value for the 1st date of each year, until 2018. Then for 2026. Don't know why 2026, I imagine there might be some relevant regulation or smth.
WEL-BrWa | 860 | .txt | 1994-01-01 | 2017-01-01 | 2025-01-01 | Quarterly | Probably |  | No |  | Similar story to Ind_Aa_and_Maas.
WEL-Ind_Br | 826 | .txt | 1976-01-01 | 2020-04-30 | 2026-01-01 | Monthly | Proably no |  | No
CHD | 11656 | .IDF | 1993-01-01 | 2018-12-28 |  | twice per month | Maybe
Note on J1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This means if the file references in some of the input files need to be extended.
Note on H2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Depends on when the KNMI TS start Reply: KNMI TS start at 2036, so there is no way to achieve continuity. Thus, the primary factor for choosing the latest date of extend is the rest of the TS files/types (e.g. if it's really hard to get accurate WEL data for the present, then we'll stick to whatever is already available.
Note on H3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Depends on when the KNMI TS start Reply: KNMI TS start at 2036, so there is no way to achieve continuity. Thus, the primary factor for choosing the latest date of extend is the rest of the TS files/types (e.g. if it's really hard to get accurate WEL data for the present, then we'll stick to whatever is already available.
Note on B4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For each parameter
Note on H4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Depends on when the KNMI TS start Reply: KNMI TS start at 2036, so there is no way to achieve continuity. Thus, the primary factor for choosing the latest date of extend is the rest of the TS files/types (e.g. if it's really hard to get accurate WEL data for the present, then we'll stick to whatever is already available.
Note on D5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: All GWAbs of this group start on the same date, even if they're 0 for a long time.
Note on E5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Same end date for all.
Note on F5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: There is an extra data point for all.
Note on H5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If we calibrate till 2018 (inc), then no. Otherwise, yes.
Note on D6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For all.
Note on E6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For all.
Note on G6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Every Jan, Apr, Jul, Oct
Note on H6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 2018 isn't included. Those are a bit number of GWAbs
Note on D7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Differs greatly. I opened some files. The first date ranged from 1961-1991.
Note on E7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Generally Apr 2020. But there are a lot of GWAbs that seem to have stopped earlier (which makes sense).
Note on H7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Depends on when the KNMI TS start Reply: KNMI TS start at 2036, so there is no way to achieve continuity. Thus, the primary factor for choosing the latest date of extend is the rest of the TS files/types (e.g. if it's really hard to get accurate WEL data for the present, then we'll stick to whatever is already available.
Note on G8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Every 14th and 28th
Note on H8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If we calibrate till 2018 (inc), then no. Otherwise, yes.

## NBr_minor
Improvement | Details | Priority | Importance | Data Requirements | Final Decision For/Against Improvement | Implementation plan | Implementation Steps
Set ICELLTYPE=1 | Currently ICELLTYPE=0 (for all layers). This means the layer saturated thickness is held constant, which is unrealistic, especially for L1. |  | 9 | -
Set Anisotropic K | Currently K=K33. Depending on the layer contents, this may be right, or totally off. E.g. K33/K a. for sand ~1, for clay/silt <<1, for fractured rock (doubt we have any of that) can vary greatly. If the calibration is good, we don't really want to mess with this. But I have a feeling it won't be. |  | 8 | K33 values/arrays
Well SS -> Transient | The current SS behaviour of wells can be improved by changing them to transient. Even non agricultural abbstractions, can fluctuate throughout the year(s), so SS is not realistic |  | 8 | GWAbs TS
Check HFB values
MetaSWAP level-controlled DRN | Investigate option to include level-controlled drainage. We may want to add this to the model.
Newton Raphson Formulation | Check if it's active. If not, consider whether we need it.

## Categories (hidden)
# | Category
1 | Process Representation
2 | Data Quality
3 | Data Resolution
4 | Parameter Estimation
5 | Spatial Resolution
6 | Temporal Resolution
7 | Model Integration
8 | Computational Efficiency
9 | Uncertainty Quantfication
10 | Calibration/Validation
11 | Data Extent
12 | Procedure Streamlining
13 | Spatial Extent
14 | QA
15 | Model Understanding

## SFR_limitations
# | Limitation | Details | Solution
1 | Wide rectangular cross-sections, with a single Manning's roughness coefficient | For regular cross-sections, it is assumed that W>>D. Hence the simplified Manning equation is used (tm6a55: 7-8 instead of 7-7), where R (hydraulic radius) is replaced with W. Also, a single Manning coefficient is used for the whole cross-section, which is a reasonable simplifiction for most cases of regular cross-sections. | Larger streams are represented well by regular cross-sections, but ditches are irregular as their width isn't much bigger than their height. MF6.3.0 added the option to model irregular cross sections, which allows for irregular cross sections to be used at later stages if model validation/calibration isn't great in areas where those features are dominant.
2 | Osciliations -unstable solution | Calculating stage and leakage with a numeric method, while they're dependent on each other, may cause instability, especially when stage and Aq head are close. | Our simulations are transient, with a small (daily) TS. This reduces the chance of oscillations. Also, the Dutch water system's predictability reduces the risk. Stage rarely raises abov the GWL, and this almost always happens in summer in predictable fashion.
3 | Streamflows are routed between stream reaches based only on continuity | Streams don't store any water! Short term effects of rapidly changing streams are innacurate. | MF6.6.0 introduced the SFR STORAGE option, which means streams can now store water.
4 | Streambed leakage is transmitted to the aquifer instantaneously | This may be problematic when there is a large head difference (10s of meters) between the stream and the aquifer. | This situation is very rare if not impossible in the Dutch water system.
5 | Variations between reaches may require more TSs | Variation in reach behaviour may require more TSs to adequately simulate the exchange of water for all model cells with a stream reach. | Daily TSs are considered sufficient with regard to variations in responses between reaches.
6 | Lack of rule-based modelling
Note on D4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Initial comment: The limitations are aknowledged. Validation will focus on simulating the processes correctly, but their timing and intensity will not be the highlight of this study. Reply: iMOD should be compatible with this new MF version. A new EXE will be sent to me. I've requested more information about what the STORAGE option does from USGS. All it says in the release notes ATM, is that it follows the logic of a similar option from an older MF version.
Note on D6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Storage term may help with that too. Reply: The STORAGE option may also counteract this to some extent as longer streams will have more room for storage.
Note on C7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: It might be possible to implement rules with the MVR package, but that is still to be explored.

## SFR_Shp_eval
In this tab I'll record which of the required SFR parameters can be extracted from the shapefiles Christopher gave me.
# | Parameter | Available? | Details
1 | ifno | calculated
2 | L | calculated
3 | R | calculated
4 | C | calculated
5 | rlen | can be extracted | Shp of 1ry and 2ry network has length field. 3ry network also has length field, but it's very inconsistent. But this can also be calculated from the geometry.
6 | rwid | can be extracted | Can be extracted from shapefile in some cases, but inconsistent. Check NotesWeeklyMeeting.docx 2025-07-08 and the scetch in Christopher's shapefile for more info.
7 | rgrd | can be extracted | Can be calculated as (Bodemhoogte bovenstrooms - Bodemhoogte benedenstrooms) / length from Open Data Portal Brabantse Delta (at least for the 1ry and 2ry Nw)
8 | rtp | can be extracted | I think the best way to do this is: (Bodemhoogte bovenstrooms - Bodemhoogte benedenstrooms)/2. But I'm not sure all segments will have a cross section at the start and end.
9 | rbth | NA | We could start with 0.3 m for tertiary ditches, 0.6 m for canals, 1 m for main rivers.
10 | rhk | NA | He didn't even mention it in his email.
11 | man | NA | Christohper used: Roughness set as Kst=30 for all water bodies (Kst = 1/n)
12 | ncon | calculated
13 | ustrf | calculated
14 | ndv | calculated
Note on D10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: There is a problem: bodemhoogste is available on website, length comes from shapefiles. We could match the cross sections to the 1ry/2ry/3ry shapefiles though.
Note on D12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SFR - RS vs Datasets for SFR

## iMOD_bugs
2 | Can't read OBS file (I had to make a my modified function to read a PRJ file with OBS) | imod python bugs/potential improvements: | Problem | Details
|  | 1 | imod.formats.prj.open_projectfile_data | doesn't return dictionary, but tuple. First item is the dict, second item is the period_data dict.
3 | SHD array cannot have nan values, even when the layer thickness is 0 (so those cells become innactive) for some reason. | 2 | loading imod takes an eternity. Modularizing it would fix that. | It's modularized, but a lot of modules use import imod instead of importing specific libraries, which makes it much slower.
|  | 3 | Can't load SS Sim where there is time in it's params. | I think time should be discarted in this case.
Note on Q2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Check source code for more.

## RscEst
# | Description | TS (days) | Sim length (years) | SPs | Layers | Rows | Cols | B per Val | HD Size (GB) | Total Size (TB) | CPU SP/h | CPU h | CPU d | Run Dur (60-core)
1 | Chaamse Beek 30 year Sim (1 enseble member) | 1 | 30 | 10950 | 37 | 344 | 480 | 4 | 249 | 0.97266 | 91.25 | 120 | 5 | 0.1
2 | Chaamse Beek 960 year run (all 8 enseble members, 4 emission Scs) | 1 | 960 | 350400 | 37 | 344 | 480 | 4 | 7975 | 31.1523 | 91.25 | 3840 | 160 | 3.2
3 | N Brabant 30 year Sim (1 ensemble member) | 1 | 30 | 10950 | 37 | 1126 | 1503 | 4 | 2554 | 9.9766 | 8.903 | 1229.9259 | 51.2469 | 1.0249
4 | N Brabant 960 year run (all 8 enseble members, 4 emission Scs) | 1 | 960 | 350400 | 37 | 1126 | 1503 | 4 | 81738 | 319.2891 | 8.903 | 39357.6279 | 1639.9012 | 32.798
5 | Chaamse Beek Vld run | 1 | 8 | 2920 | 37 | 344 | 480 | 4 | 66 | 0.25781 | 91.25 | 32 | 1.3333 | 0.026667
6
7
8
9
10
|  |  |  | HD size calc | [6 empty] | Researc cloud storage cost calcs
|  |  |  | SPs | Layers | Rows | Cols | B per Val | HD Size (GB) |  | Storage (TB) | Duration (days) | Cost (credits) | Cost/storage/day
|  |  |  | 3285 | 37 | 344 | 480 | 8 | 149.5 |  | 0.99609 | 150 | 3473.1 | 23.2448
[11 empty] | 0.49316 | 150 | 1719.5 | 23.2445
[11 empty] | 0.49316 | 300 | 3439.1 | 23.2451
Note on J1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Just for the .HED file
Note on K1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Rough estimate, as I'm not sure about all the outputs that'll be produced.
Note on O1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Assuming 50x speed-up over 1 core.
Note on L2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Based on NBr5 (I'm hoping this is an overestimate, as Research cloud should be much faster than OneDrive).
Note on J14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Just for the .HED file

## SFR_extra_system_error (hidden)
Let's compare total WB components from two runs that are identical besides the SFR. We're doing this cause we noticed that when the SRF is added, CHD and DRN components for systems below L1 disappear.
We'll compare NBr23 (B) to NBr24 (S). NBr23 is a 3 SP Hi run. NBr24 is identical to NBr24, but with the SFR added (but the rtp I so high that there shouldn't be any water exchange).
VOLUME BUDGET FOR ENTIRE MODEL AT END OF TIME STEP 1, STRESS PERIOD 2
---------------------------------------------------------------------------------------------------
| NBr23 |  |  |  | NBr24
| IN |  |  |  | IN
| CUMULATIVE VOLUME |  | L**3 |  | CUMULATIVE VOLUME |  | L**3 | SmB | SmBpB*100
| IN: |  |  | IN: |  |  | IN:
| --- |  |  | --- |  |  | ---
| STO-SS | = | 85372.4493 |  | STO-SS | = | 85372.4493 | 0 | 0
| WEL | = | 0 |  | WEL | = | 0 | 0 | #DIV/0!
| WEL | = | 0 |  | WEL | = | 0 | 0 | #DIV/0!
| DRN | = | 0 |  | DRN | = | 0 | 0 | #DIV/0!
| RIV | = | 1.1268 |  | RIV | = | 1.1268 | 0 | 0
| RCH | = | 730030.9459 |  | RCH | = | 730030.9459 | 0 | 0
| CHD | = | 49526.385 |  | CHD | = | 49526.385 | 0 | 0
[5 empty] | SFR | = | 0
| TOTAL IN | = | 864930.907 |  | TOTAL IN | = | 864930.907 | 0 | 0
| OUT: | OUT: |  |  | OUT: | OUT:
| ---- | ---- |  |  | ---- | ----
| STO-SS | = | 628508.8924 |  | STO-SS | = | 628508.8924 | 0 | 0
| WEL | = | 30344.6523 |  | WEL | = | 30344.6523 | 0 | 0
| WEL | = | 3355.8359 |  | WEL | = | 3355.8359 | 0 | 0
| DRN | = | 26518.0711 |  | DRN | = | 26518.0711 | 0 | 0
| RIV | = | 31860.2434 |  | RIV | = | 31860.2434 | 0 | 0
| RCH | = | 75077.1545 |  | RCH | = | 75077.1545 | 0 | 0
| CHD | = | 69409.9867 |  | CHD | = | 69409.9867
[5 empty] | SFR | = | 0
| TOTAL OUT | = | 865074.8364 |  | TOTAL OUT | = | 865074.8364 | 0 | 0
THIS IS NO ERROR. IT'S JUST THAT IN ONE RUN I USED THE SSYSTEM OPTION AND IN ANOTHER ONE I DIDN'T…

## SFR_extra_system_error (2) (hidden)
Let's compare total WB components from two runs that are identical besides the SFR. We're doing this cause we noticed that when the SRF is added, CHD and DRN components for systems below L1 disappear.
We'll compare NBr23 (B) to NBr24 (S). NBr23 is a 3 SP Hi run. NBr24 is identical to NBr24, but with the SFR added (but the rtp I so high that there shouldn't be any water exchange).
VOLUME BUDGET FOR ENTIRE MODEL AT END OF TIME STEP 1, STRESS PERIOD 2
---------------------------------------------------------------------------------------------------
| NBr23 |  |  |  | NBr24
| IN |  |  |  | IN
| CUMULATIVE VOLUME |  | L**3 |  | CUMULATIVE VOLUME |  | L**3 | SmB | SmBpB*100
| IN: |  |  | IN: |  |  | IN:
| --- |  |  | --- |  |  | ---
| STO-SS | = | 85372.4493 |  | STO-SS | = | 82156.3885 | -3216.0608 | -3.7671
| WEL | = | 0 |  | WEL | = | 0
| WEL | = | 0 |  | DRN | = | 0
| WEL | = | 0 |  | RIV | = | 1.1268 | 0 | 0
| WEL | = | 0 |  | RCH | = | 730016.607 | -14.3389 | -0.0019641
| DRN | = | 0 |  | CHD | = | 47252.0586 | -2274.3264 | -4.5922
| DRN | = | 0 |  | SFR | = | 0
| DRN | = | 0
| RIV | = | 0 |  | TOTAL IN | = | 859426.181 | -5504.726 | -0.63644
| RIV | = | 0
| RIV | = | 0
| RIV | = | 0
| RIV | = | 1.1268
| RCH | = | 730030.9459
| CHD | = | 530.326
| CHD | = | 3913.6963
| CHD | = | 2842.8613
| CHD | = | 1014.8166
| CHD | = | 778.738
| CHD | = | 1332.8432
| CHD | = | 516.8815
| CHD | = | 1186.6908
| CHD | = | 2091.6387
| CHD | = | 5208.4462
| CHD | = | 1631.9171
| CHD | = | 6871.9678
| CHD | = | 4820.8257
| CHD | = | 0
| CHD | = | 0
| CHD | = | 0
| CHD | = | 60.3783
| CHD | = | 7267.0292
| CHD | = | 9457.3283
| TOTAL IN | = | 864930.907
| OUT: | OUT: |  |  | OUT: | OUT:
| ---- | ---- |  |  | ---- | ----
| STO-SS | = | 628508.8924 |  | STO-SS | = | 639366.2569 | 10857.3645 | 1.7275
| WEL | = | 0 |  | WEL | = | 3355.8359
| WEL | = | 0 |  | DRN | = | 26519.6548 | 1.5837 | 0.0059722
| WEL | = | 30344.6523 |  | RIV | = | 31881.7738 | 21.5304 | 0.067578
| WEL | = | 3355.8359 |  | RCH | = | 75084.6675 | 7.513 | 0.010007
| DRN | = | 21057.3965 |  | CHD | = | 83056.4631 | 13646.4763 | 19.6607
| DRN | = | 969.4308 |  | SFR | = | 0
| DRN | = | 4491.2438
| RIV | = | 31860.2434 |  | TOTAL OUT | = | 859264.652 | -5810.1844 | -0.67164
| RIV | = | 0
| RIV | = | 0 |  | IN | - | OUT
| RIV | = | 0
| RIV | = | 0 |  | PERCENT | DISCREPANCY | =
| RCH | = | 75077.1545
| CHD | = | 3471.5511
| CHD | = | 800.5205
| CHD | = | 2378.2731
| CHD | = | 5032.6646
| CHD | = | 2443.7286
| CHD | = | 2738.406
| CHD | = | 1244.4767
| CHD | = | 1689.0364
| CHD | = | 4631.8999
| CHD | = | 2115.9993
| CHD | = | 3695.448
| CHD | = | 3832.8203
| CHD | = | 6525.938
| CHD | = | 0
| CHD | = | 0
| CHD | = | 0
| CHD | = | 52.5762
| CHD | = | 23411.4585
| CHD | = | 5345.1896
| TOTAL OUT | = | 865074.8364